**Understanding and building the gender intersectionality landscape for the prevention of antimicrobial resistance in Sierra Leone-The UB-GILPAR Project**

**Key Decision-Making Bodies:**

1. **Scientific Committee**: Composed of Principal Investigators and Co-principal investigators and Research Coordinator. They have the ultimate decision-making authority. They approve major milestones, budgets, and any changes in scope.
2. **Project Team**: Comprised of Research Coordinator, Project Coordinator, and Finance team provides strategic advice but does not have binding decision-making powers.
3. **Project Coordinator**: Responsible for the day-to-day management, the Project Coordinator makes operational decisions within the framework set by the Scientific Committee and Project team.

**Coordination Meetings:**

* **Quarterly Meetings**: Conducted by the Project Scientific Committee to review project status and make high-level decisions.
* **Bi-annual Meetings**: The Project Team meets to offer strategic advice.
* **Monthly Team Meetings**: Led by the Project Coordinator for operational decisions and status updates.
* **Weekly Technical Meetings**: For in-depth discussions on technical challenges and solutions.

**Organizational Chart:**

The organizational chart, depicted earlier, illustrates the hierarchical structure and reporting relationships within the project.

A diagram of a project

Description automatically generated

**Monitoring:**

The Monitoring & Evaluation Team will employ The Key Performance Indicators (KPIs) to assess the project's progress against its objectives. From time-to-time reports will be generated and reviewed in coordination meetings.