|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Activities | Year 1 | | | | Year 2 | | | |
|  | Q1 | Q2 | Q3 | Q4 | QI | Q2 | Q3 | Q4 |
| Project Initiation | X |  |  |  |  |  |  |  |
| Conduct surveys and interviews | X | X |  |  |  |  |  |  |
| Building of the AbuSensebod Prototype | X | X |  |  |  |  |  |  |
| Develop AI Models | X | X | X |  |  |  |  |  |
| Analyze Diagnostics Data |  | X | X |  |  |  |  |  |
| AI Model Training |  | X | X | X |  |  |  |  |
| Draft Report |  |  |  | X |  |  |  |  |
| Finalize Prototype |  |  |  | X |  |  |  |  |
| Complete initial AI Models |  |  |  | X |  |  |  |  |
| Pilot AbuSensebod |  |  |  |  | X | X |  |  |
| Gather Pilot feedback |  |  |  |  | X | X |  |  |
| Refine AI models |  |  |  |  | X |  |  |  |
| Analyze Pilot Data |  |  |  |  |  | X | X |  |
| Workshops to share insights |  |  |  |  |  | X |  |  |
| Evaluate Outcomes |  |  |  |  |  |  | X | X |
| Deploy and launch AbuSensebod |  |  |  |  |  |  |  | X |
| Publish Research |  |  |  |  |  |  |  | X |
| Policy Briefings |  |  |  |  |  |  |  | X |