## CIHR Work Plan
| Color Key: | Activity in Progress
Target Date for Completion or Key Decision Point
Date Activity was Completed
Activity is PAST DUE
Understanding and building the gender intersectionality landscape for the prevention of antimicrobial resistance in Sierra Leone
Main Activities | Activities (& Process Targets) | Person(s) Responsible | Senior Leadership Person Responsible | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01
Project Planning | Define objectives | PI | Dr. Lakoh
| Assemble team | PI | Dr. Lakoh
| Validate study protocol and tools with stakeholders | Research Coordinator | Dr. Lakoh
Ethics Approval | Prepare documents | Research Coordinator | Dr. Lakoh
| Submit to ethics Committee | Project Coordinator | Bailah
| Obtain approval | Project Coordinator | Bailah
Desk Review and Protocol Development | Development of the protocol for the desk review of literature | Research Coordinator | Dr. Lakoh
| Desk review of the literature | Research Coordinator | Dr. Lakoh
| Coding of the data from the desk review | Research Coordinator | Dr. Lakoh
Qualitative Research and Manuscript Writing | Protocol and interview guide development | Dr. Lakoh | Dr. Lakoh
| Key informant interviews | Project Coordinator | Bailah
| Transcription Data analysis | Research Coordinator | Joseph Sam Kanu
| Manuscript writing | PI | Joseph Sam Kanu
Stakeholder engagement and Capacity Building | Stakeholder engagement | Project Coordinator | Bailah
| Training and Awareness raising | Project Coordinator | Dr. Jiba
Road map Development | Consultative meeting with key actors | Project Coordinator | Dr Matilda Kamara
| Consensus Building | Project Coordinator | Dr. Jiba
| Meeting with stakeholders to develop the roadmap on gender intersectionality | Research Coordinator | Dr Lakoh
Report Preparation and Submission | Submit report to TDR | PI | Dr Lakoh
| Publish findings in open-access peer-reviewed journals | PI | Dr Lakoh
| Present findings at national and international conferences | PI | Dr Lakoh
Dissemination and Training | Prepare and distribute policy briefs, information leaflets, and social media content | Research Coordinator | Dr. Lakoh
| Knowleddge users meeting-Dissemination | Joseph Sam Kanu | Dr. Lakoh

## Wokplan Mini
AMR Landscap Scooping in Sierra Leone
Years | Year 1 |  |  |  | Year 2
Quarters | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Project Planning and Initialization
Ethics Application
Desk Review and Protocol Development
Qualitative Research and Manuscript Writing
Stakeholder Engagement and Capacity Building
Roadmap Development
Report Preparation and Submission
Dissemination and Training